## Dark
TERT Review Paper
Usask |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Jared Price
Project Start Date: | 2022-10-31 |  |  |  |  | November | [34 empty] | December
Scrolling Increment: | 1 | time axis 2022-11-01 to 2022-12-26
Milestone description | Category | Assigned to | Progress | Start | Days | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
Paper Progress
Skeleton Prepared | On Track | Jared | 5% | 2022-10-31 | 2
Skeleton Accepted | Goal | Behzad | 6% | 2022-11-05 | 1 | S: 2
Library Consult | Goal | Jared | 10% | 2022-11-06 | 1 | S: 2
Accumulate 25 Papers | Goal | Jared | 15% | 2022-11-07 | 2 | M: 2; T: 2
Accumulate 50 Papers | Goal | Jared | 20% | 2022-11-09 | 2 | W: 2; T: 2
Accumulate 75 Papers | Goal | Jared | 25% | 2022-11-10 | 2 | T: 2; F: 2
Accumulate 100 Papers | Goal | Jared | 30% | 2022-11-11 | 4 | F: 2; S: 2; S: 2; M: 2
Complete Background Section | Goal | Jared | 40% | 2022-11-15 | 4 | T: 2; W: 2; T: 2; F: 2
Complete Telomerase Section | Goal | Jared | 50% | 2022-11-19 | 4 | S: 2; S: 2; M: 2; T: 2
Complete SLI/SLDI Section | Goal | Jared | 60% | 2022-11-23 | 5 | W: 2; T: 2; F: 2; S: 2; S: 2
Verify First Draft | Goal | Behzad | 70% | 2022-11-28 | 5 | M: 2; T: 2; W: 2; T: 2; F: 2
ReVerify First Draft | Goal | Andrew | 80% | 2022-12-03 | 3 | S: 2; S: 2; M: 2
Submit To Cells | Goal | Jared | 90% | 2022-12-06 | 10 | T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2
Complete Outstanding Requirements | Goal | Jared | 100% | 2022-12-16 | 1 | F: 2
To add more data, Insert new rows ABOVE this one